15 May 2025

Road Works Notice

Great North Road Improvements Project – Date Change

Kia ora,

There has been a change to the start date of stage 3. It will now start in early June. There are a number of contributing factors to this change including bad weather. We apologise for the change in date and the inconvenience this may cause.

We have programmed the remaining work for the current stage to minimise disruption to the community. We plan to open access to closed side streets sequentially. The first road will be opened at the end of next week and others will follow until they are all open by 6 June 2025.

There is no change to how stage 3 will be carried out. Details are as previously advertised.

| Where | Two locations on Great North Road, both sides of the road: - between Nixon Street and Mackelvie Street. - between Brisbane Street and King Street |
| --- | --- |
| When | 6 June 2025 – late Aug 2025 |
| Hours of work | 7am to 7pm, Monday – Friday 7am to 6pm, Saturday (as required) |

New Site Set Up – Night Works

The existing sites will be disestablished and new sites set up on Thursday 5 June 2025. Fences and temporary traffic management will be removed, and line marking installed in the completed areas between Mackelvie Street and Sussex Street, Northland Street and Crummer Road. This work will be done 5:30pm - 11:00pm.

Traffic management for the new sites will then be set up. New road line marking will be installed to support traffic flow around our work sites. This will be done Thursday 5 June – 5:00am Friday 6 June. These two sections of Great North Road will be closed to all traffic except buses during this time. There will be detours in place, please follow on street signage. This is not particularly noisy work but there will be vehicle movements and loading/unloading of trucks.  This work may be postponed in the event of bad weather.

Main Works – What to Expect

Detours and intersection (side street entry) closures

- There will be no entry to the following side streets from Great North Rd: Pollen St, Mackelvie St, Turakina St, Ariki St and Potatau St. Please follow detour signs to the next accessible side street.

- Entry to Nixon St will be left turn only from Great North Rd. There will be no exit from Nixon St onto Great North Rd. Exit out of Nixon St and Burgoyne St will be via Chapman St, which will be two-way during the construction period.

- Entry to Burns St will be a left turn only from Great North Rd. Exit from Burns St will be via Putiki St and Kirk St.

- Construction at intersections between Brisbane St and King St will be staggered. Brisbane St will be completed first, then King St and lastly Potatau St. During construction at Brisbane St, vehicle access to the top of the street will be open from Dean St.

- Entry to King St will be a left turn only from Great North Rd. King St can be accessed via Potatau St and Dean St. Exit from King St will be via Dean St. To allow for large vehicles along Dean St, there will be no parking on the northern side of the street.

See www.AT.govt.nz/greatnorthroad for detour details.

Staging Plan (please note timelines are indicative and may change)

Sign Up for Project Updates

We’ll be sharing regular updates via email – please sign up using the QR code or email Projects@at.govt.nz.

Contact Us

If you have any queries about this project, please contact AT:

Email: Projects@at.govt.nz or Phone: 09 930 5090

If you have any queries related to construction, please contact JFC Ltd.

Stakeholder Liaison Manager: Sally Logan

Email: Sally.Logan@jfcltd.co.nz  or  Phone: 021 420 794

To learn more about this project please visit www.AT.govt.nz/greatnorthroad

We apologise in advance for any inconvenience this may cause and appreciate your patience and understanding during the works.

Ngā mihi,

The Great North Road Improvements Project Team